## Nine Dimensions
Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix | Feature Nine-Dimension Progress Matrix
One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages. | One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages.
Dimension | Average | 100% features | Applicable features | Primary gap
Design doc | 30% | 3 | 10 | F-004 to F-010 need dedicated design sources after F-003 capture
Numeric table | 30% | 3 | 10 | F-004 to F-010 need original configuration tables
Code | 30% | 3 | 10 | Only F-001 to F-003 have runtime behavior
Scene | 12.5% | 1 | 8 | Future scene decisions remain unsourced
UI | 30% | 3 | 10 | Future object-first UI contracts remain unsourced
Icon/image | 12.5% | 1 | 8 | Future visual asset contracts remain unsourced
Scene integration | 12.5% | 1 | 8 | Future scene integration remains unsourced
Image integration | 12.5% | 1 | 8 | Future image integration remains unsourced
UI integration | 20% | 2 | 10 | F-003 reviewed capture pending; future UI integration not started
Feature total | 28% | 2 | 10 | F-003 evidence blocked; F-004 to F-010 roadmap-only
Feature ID | Complete feature | Source type | Functional source | Numeric/config source | Producer directive | Priority | Design doc | Numeric table | Code | Scene | UI | Icon/image | Scene integration | Image integration | UI integration | Overall | Current stage | Owner | Next milestone | Blocker/dependency
F-003 | Animal Town Farm Foundation V2 | Original animal-town farm production foundation | docs/features/F-003-farm-town-foundation-v2.md | config/tables/f003_v2_items,crops,storage,recipes,animals,buildings,requests,world,locale.csv | F003-FARM.2: 12 plots, animal care, machine queues, requests, market, and a draggable 1800 x 1700 town | P0 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | ACCEPTED PLAYABLE PROTOTYPE | Codex /root | Start F-004 formal design intake | F003-FARM2-ENG-002: five real 720 x 1280 captures, 26 runtime assets, behavior tests and normal startup passed; no F-004 runtime authority
F-004 | Farm District Board and Industry I | Original farm-town roadmap | docs/roadmaps/PLAN-001-original-farm-town-content-ladder.md | Pending dedicated configuration source | MARKET-FARMTOWN.1: farm districts, feed, animals, and Industry I before logistics | P0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | NEXT FORMAL DESIGN INTAKE | Codex /root | Create F-004 general feature doc, editable Figma, and dedicated configuration sources | F-003 accepted; F-004 runtime still requires its own source, receipt, write set, and behavior evidence
F-005 | Rail Freight Yard | Original farm-town roadmap | docs/roadmaps/PLAN-001-original-farm-town-content-ladder.md | Pending dedicated configuration source | MARKET-FARMTOWN.1: multi-good rail freight is the mid-horizon order channel | P0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ROADMAP ONLY | Codex /root | Create F-005 functional/config source after F-004 acceptance | F-004 acceptance and dedicated source/receipt/authorization
F-006 | Town Trade Quarter and Industry II | Original farm-town roadmap | docs/roadmaps/PLAN-001-original-farm-town-content-ladder.md | Pending dedicated configuration source | MARKET-FARMTOWN.1: town services plus cross-linked Industry II | P1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ROADMAP ONLY | Codex /root | Create F-006 functional/config source after F-005 acceptance | F-005 acceptance and dedicated source/receipt/authorization
F-007 | Sky Cargo Harbor | Original farm-town roadmap | docs/roadmaps/PLAN-001-original-farm-town-content-ladder.md | Pending dedicated configuration source | MARKET-FARMTOWN.1: long-horizon mixed cargo batch | P1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ROADMAP ONLY | Codex /root | Create F-007 functional/config source after F-006 acceptance | F-006 acceptance and dedicated source/receipt/authorization
F-008 | Land and District Expansion | Original farm-town roadmap | docs/roadmaps/PLAN-001-original-farm-town-content-ladder.md | Pending dedicated configuration source | MARKET-FARMTOWN.1: functional space, building sites, and route choices | P1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ROADMAP ONLY | Codex /root | Create F-008 functional/config source after F-007 acceptance | F-007 acceptance and dedicated source/receipt/authorization
F-009 | Riverbank and Stoneworks | Original farm-town roadmap | docs/roadmaps/PLAN-001-original-farm-town-content-ladder.md | Pending dedicated configuration source | MARKET-FARMTOWN.1: integrated side-resource and construction branch | P2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ROADMAP ONLY | Codex /root | Create F-009 functional/config source after F-008 acceptance | F-008 acceptance and dedicated source/receipt/authorization
F-010 | Collections and Cooperative Layer | Original farm-town roadmap | docs/roadmaps/PLAN-001-original-farm-town-content-ladder.md | Pending dedicated configuration source | MARKET-FARMTOWN.1: defer collections/co-op until solo core is content-complete | P3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ROADMAP ONLY | Codex /root | Make separate product decision after F-009 acceptance | F-009 acceptance plus separate product decision and dedicated source
F-001 | Market Meadow P0 | Original technical P0 | docs/features/F-001-market-meadow-p0.md | config/tables/f001_market_meadow.csv | Commercial-safe original loop; emoji/SVG placeholders only | P0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | COMPLETE | Codex /root | Select next priority feature | None - F-001 accepted
F-002 | Farmboard Visual Language | Original visual UX slice | docs/features/F-002-farmboard-visual-language.md | config/tables/f002_town_ui.csv | Original object-first Farmboard; zh-CN default and English Settings | P0 | 1 | 1 | 1 | Not needed | 1 | Not needed | Not needed | Not needed | 1 | 1 | COMPLETE | Codex /root | Select next priority feature | None - F-002 accepted

## Overview
Project Progress Overview | Project Progress Overview | Project Progress Overview | Project Progress Overview
Active features | Exceptions | Ready roles | Next work
1 | 1 | 1 | Capture reviewed F-003 720 x 1280 runtime image

## Active Batch
Active Batch | Active Batch | Active Batch | Active Batch | Active Batch | Active Batch | Active Batch | Active Batch
Priority | Task | Task ID | Owner | State | Last verified progress | Next milestone | Exception
P0 | Herd and Local Orders | F003-ENG-001-IMPL | Codex /root | EVIDENCE BLOCKED | Model test and normal startup passed | Capture reviewed runtime image | Existing Godot error dialog blocks capture

## Role Capacity
Role Capacity | Role Capacity | Role Capacity | Role Capacity | Role Capacity | Role Capacity
Role | Role ID | Load | Availability | Next assignment | Producer action
Producer | producer | 1 | Occupied | F-003 capture closure | Keep one writer and verify reviewed visual evidence
Design owner | design-owner | 1 | Occupied | F-003 capture review | Hold F-004/F-005 as roadmap only
Engineering owner | engineering-owner | 1 | Occupied | F-003 visual capture | Keep runtime behavior stable during capture
Art owner | — | 0 | Available | — | No separate art task; vector placeholders are approved
PM execution operator | pm-ops | 0 | Available | Matrix refresh after close | Keep normal checks quiet

## Update Rules
Update Rules | Update Rules | Update Rules | Update Rules
Rule | Current behavior | Owner | Formal source
Exception check | Short interval; current batch only; healthy checks quiet | PM execution operator | docs/active_scope.yaml
Workbook refresh | Every 6 hours or on producer request; save only changes | PM execution operator | docs/active_scope.yaml
Work order | Priority first; same priority by feature ID; completed last | Producer | PM/feature_progress.xlsx
Not applicable | Display Not needed and exclude from averages | PM execution operator | Nine Dimensions
Write boundary | Operator writes only this workbook | PM execution operator | docs/WORKFLOW.md