## Nine Dimensions
Feature Nine-Dimension Progress Matrix
One row is one complete feature. Sort by priority, then feature ID; completed rows go last. Non-applicable dimensions display Not needed and are excluded from averages.
Dimension | Average | 100% features | Applicable features | Primary gap
Design doc | 45.45% | 5 | 11 | F004.2 design, Penpot, runtime and visual gates passed; F-005 to F-010 require dedicated design sources
Numeric table | 45.45% | 5 | 11 | F004.2 twelve-table configuration set passed; F-005 to F-010 retain configuration gaps
Code | 45.45% | 5 | 11 | F004.2 independent model/view/save implementation passed; F-005 to F-010 retain code gaps
Scene | 45.45% | 5 | 11 | F004.2 main, slice and rollback scenes passed; F-005 to F-010 retain scene gaps
UI | 45.45% | 5 | 11 | F004.2 native 720x1280 UI and complete states passed; F-005 to F-010 retain UI gaps
Icon/image | 45.45% | 5 | 11 | F004.2 approved asset set passed in runtime; F-005 to F-010 retain icon/image gaps
Scene integration | 45.45% | 5 | 11 | F004.2 scene integration passed real runtime evidence; F-005 to F-010 retain integration gaps
Image integration | 45.45% | 5 | 11 | F004.2 approved-only image integration passed leak checks; F-005 to F-010 retain integration gaps
UI integration | 45.45% | 5 | 11 | F004.2 touch/state/localization/reduced-motion integration passed; F-005 to F-010 retain UI integration gaps
Feature total | 45.45% | 5 | 11 | F004.2 is closed; no feature is active and F-005 remains ROADMAP_ONLY pending a dedicated intake
Feature ID | Complete feature | Source type | Functional source | Numeric/config source | Producer directive | Priority | Design doc | Numeric table | Code | Scene | UI | Icon/image | Scene integration | Image integration | UI integration | Overall | Current stage | Owner | Next milestone | Blocker/dependency
F-003 | Animal Town Farm Foundation V2 | Original animal-town farm production foundation | docs/features/F-003-farm-town-foundation-v2.md | config/tables/f003_v2_items,crops,storage,recipes,animals,buildings,requests,world,locale.csv | F003-FARM.2: 12 plots, animal care, machine queues, requests, market, and a draggable 1800 x 1700 town | P0 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | ACCEPTED PLAYABLE PROTOTYPE | Codex /root | Start F-004 formal design intake | F003-FARM2-ENG-002: five real 720 x 1280 captures, 26 runtime assets, behavior tests and normal startup passed; no F-004 runtime authority
F-004 | Animal Resident Town Spatial & Autonomy Foundation | Producer-approved resident-town representative runtime slice / verified Penpot editable handoff | docs/features/F-004-resident-town-spatial-autonomy.md; docs/evidence/F004-RESIDENT.1/README.md; output/penpot/F004-RESIDENT.1/README.md | config/tables/f004_resident_grid.csv; f004_resident_types.csv; f004_resident_jobs.csv; f004_resident_workplaces.csv; f004_vehicle_orders.csv; f004_vehicle_routes.csv; f004_resident_locale.csv | PD-002 + PD-003 / F004-RESIDENT.1 V1.2: visible residents autonomously work and fulfill a world-vehicle order; representative slice approved | P0 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | RUNTIME_SLICE_APPROVED / SCALE_OUT_NOT_AUTHORIZED | Codex /root | F004.1 preserved as the accepted rollback baseline; F004.2 now owns quality scale-out | None for the accepted representative slice; no runtime lock is active
F-004.2 | Resident Dairy Neighborhood & Daily Life Scale-Out | Producer-approved F004 quality scale-out / editable Penpot / approved asset set / independent Godot runtime accepted | docs/features/F-004-resident-dairy-neighborhood-scaleout.md; docs/evidence/F004-RESIDENT.2/README.md; docs/receipts/F004-RESIDENT-SCALEOUT-RUNTIME-ACCEPTANCE-016.md | config/tables/f004_resident2_grid,objects,residents,jobs,workplaces,tasks,orders,routes,schedules,visuals,audio,locale.csv | PD-004 / F004-RESIDENT.2: actual footprint placement, second bear resident, dairy work and visible daily life | P0 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | RUNTIME_SLICE_APPROVED / SCALE_OUT_APPROVED | Codex /root | Closed; create a separate feature identity and gate for the next approved scale-out | None; no active shared lock and F004.1 remains the explicit rollback scene
F-005 | Rail Freight Yard | Original farm-town roadmap | docs/roadmaps/PLAN-001-original-farm-town-content-ladder.md | Pending dedicated configuration source | MARKET-FARMTOWN.1: multi-good rail freight is the mid-horizon order channel | P0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | ROADMAP ONLY | Codex /root | Create F-005 functional/config source after F004-RESIDENT.2 scale-out acceptance | Skipped while user-authorized F004.2 footprint/resident/multi-building quality gaps are active
F-006 | Town Trade Quarter and Industry II | Original farm-town roadmap | docs/roadmaps/PLAN-001-original-farm-town-content-ladder.md | Pending dedicated configuration source | MARKET-FARMTOWN.1: town services plus cross-linked Industry II | P1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ROADMAP ONLY | Codex /root | Create F-006 functional/config source after F-005 acceptance | F-005 acceptance and dedicated source/receipt/authorization
F-007 | Sky Cargo Harbor | Original farm-town roadmap | docs/roadmaps/PLAN-001-original-farm-town-content-ladder.md | Pending dedicated configuration source | MARKET-FARMTOWN.1: long-horizon mixed cargo batch | P1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ROADMAP ONLY | Codex /root | Create F-007 functional/config source after F-006 acceptance | F-006 acceptance and dedicated source/receipt/authorization
F-008 | Land and District Expansion | Original farm-town roadmap | docs/roadmaps/PLAN-001-original-farm-town-content-ladder.md | Pending dedicated configuration source | MARKET-FARMTOWN.1: functional space, building sites, and route choices | P1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ROADMAP ONLY | Codex /root | Create F-008 functional/config source after F-007 acceptance | F-007 acceptance and dedicated source/receipt/authorization
F-009 | Riverbank and Stoneworks | Original farm-town roadmap | docs/roadmaps/PLAN-001-original-farm-town-content-ladder.md | Pending dedicated configuration source | MARKET-FARMTOWN.1: integrated side-resource and construction branch | P2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ROADMAP ONLY | Codex /root | Create F-009 functional/config source after F-008 acceptance | F-008 acceptance and dedicated source/receipt/authorization
F-010 | Collections and Cooperative Layer | Original farm-town roadmap | docs/roadmaps/PLAN-001-original-farm-town-content-ladder.md | Pending dedicated configuration source | MARKET-FARMTOWN.1: defer collections/co-op until solo core is content-complete | P3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ROADMAP ONLY | Codex /root | Make separate product decision after F-009 acceptance | F-009 acceptance plus separate product decision and dedicated source
F-001 | Market Meadow P0 | Original technical P0 | docs/features/F-001-market-meadow-p0.md | config/tables/f001_market_meadow.csv | Commercial-safe original loop; emoji/SVG placeholders only | P0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | COMPLETE | Codex /root | Select next priority feature | None - F-001 accepted
F-002 | Farmboard Visual Language | Original visual UX slice | docs/features/F-002-farmboard-visual-language.md | config/tables/f002_town_ui.csv | Original object-first Farmboard; zh-CN default and English Settings | P0 | 1 | 1 | 1 | Not needed | 1 | Not needed | Not needed | Not needed | 1 | 1 | COMPLETE | Codex /root | Select next priority feature | None - F-002 accepted

## Overview
Project Progress Overview
Active features | Exceptions | Ready roles | Next work
0 | 0 | 5 | No active write task; next work requires a dedicated approved feature intake

## Active Batch
Active Batch
Priority | Task | Task ID | Owner | State | Last verified progress | Next milestone | Exception
- | No active write task |  | Codex /root | IDLE | F004.2 runtime, visual, performance and regression acceptance complete | Separate next-feature intake | No active shared lock

## Role Capacity
Role Capacity
Role | Role ID | Load | Availability | Next assignment | Producer action
Producer | producer | 0 | Available | Review next approved feature intake | Keep one accountable producer
Design owner | design-owner | 0 | Available | Await next approved design scope | Preserve Penpot and observable-rule gates
Engineering owner | engineering-owner | 0 | Available | Await next approved runtime scope | Require a new read-only receipt and exact write set
Art owner | art-owner | 0 | Available | Await next approved asset scope | Keep one-set and approved-only asset gates
PM execution operator | pm-ops | 0 | Available | Await next approved control-plane scope | Refresh RAG only after source changes

## Update Rules
Update Rules
Rule | Current behavior | Owner | Formal source
Exception check | Short interval; current batch only; healthy checks quiet | PM execution operator | docs/active_scope.yaml
Workbook refresh | Every 6 hours or on producer request; save only changes | PM execution operator | docs/active_scope.yaml
Work order | Priority first; same priority by feature ID; completed last | Producer | PM/feature_progress.xlsx
Not applicable | Display Not needed and exclude from averages | PM execution operator | Nine Dimensions
Write boundary | Operator writes only this workbook | PM execution operator | docs/WORKFLOW.md